## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Finding Pluto |  |  |  |  | SOFTWARE DEVELOPMENT AND TOOLS
TEAM MEMBERS |  | Veda, Chandler, Jaylee, Jack, Sam, Suyogya |  |  |  |  | DATE | [6 empty] | 2021-02-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1.1 | Registration Page | Jack | 2021-02-19 | 2021-03-01 | 1 | bar: WEEK 2 W
1.2 | Login Page | Jaylee | 2021-02-19 | 2021-03-01 | 1 | bar: WEEK 2 W to WEEK 2 F
1.3 | Play level page | Suyogya | 2021-02-23 | 2021-03-19 | 1 | bar: WEEK 2 R to WEEK 2 F
1.4 | Browse level page | Veda | 2021-02-24 | 2021-03-24 | 1
1.5 | Level Designer page | Sam/Chandler | 2021-02-24 | 2021-03-24 | 1